## Clients
01. Client Details
Client ID | Client Name (Company) | Name of Point of Contact | Mobile No. | Landline No. | Email | Address | Status | Comments / Notes
CLNT1001 | XYZ Enterprises | Olivia Miller | 1112223336 | 021-11111114 | olivia.miller@example.com | 369 Pine St | Active | Responsive communication
CLNT1002 | ABC Solutions | Ethan Wilson | 2223334447 | 021-22222225 | ethan.wilson@example.com | 789 Cedar St | Active | Regular updates
CLNT1003 | DEF Tech | Lily Turner | 3334445558 | 021-33333336 | lily.turner@example.com | 456 Elm St | Inactive | Contract expired
CLNT1004 | GHI Innovations | Noah Brown | 4445556669 | 021-44444447 | noah.brown@example.com | 101 Pine St | Active | Excellent collaboration
CLNT1005 | JKL Enterprises | Ava Smith | 5556667780 | 021-55555558 | ava.smith@example.com | 246 Cedar St | Active | Satisfied with services
CLNT1006 | MNO Solutions | Mia Turner | 6667778891 | 021-66666669 | mia.turner@example.com | 135 Elm St | Active | Timely deliveries
CLNT1007 | PQR Tech | Oliver Adams | 7778889992 | 021-77777780 | oliver.adams@example.com | 246 Pine St | Inactive | Contract renewal pending
CLNT1008 | STU Enterprises | Chloe Parker | 8889990003 | 021-88888891 | chloe.parker@example.com | 987 Walnut St | Active | Reliable service
CLNT1009 | VWX Innovations | Liam Brown | 9990001114 | 021-99999903 | liam.brown@example.com | 654 Maple St | Active | Efficient communication
CLNT1010 | YZ Tech | Emma Wilson | 1112225 | 021-00000014 | emma.wilson@example.com | 321 Elm St | Active | Positive feedback
CLNT1011 | QRS Solutions | Ethan Miller | 1112223335 | 021-11111113 | ethan.miller@example.com | 369 Cedar St | Active | Responsive communication
CLNT1012 | TUV Innovations | Lily Garcia | 2223334446 | 021-22222224 | lily.garcia@example.com | 789 Pine St | Active | Regular updates
CLNT1013 | WXY Enterprises | Noah Turner | 3334445557 | 021-33333335 | noah.turner@example.com | 456 Walnut St | Inactive | Contract expired
CLNT1014 | ZAB Tech | Ava Brown | 4445556668 | 021-44444446 | ava.brown@example.com | 101 Elm St | Active | Excellent collaboration
CLNT1015 | CDE Innovations | Mia Smith | 5556667779 | 021-55555557 | mia.smith@example.com | 246 Cedar St | Active | Satisfied with services
CLNT1016 | FGH Solutions | Oliver Adams | 6667778890 | 021-66666668 | oliver.adams@example.com | 135 Pine St | Active | Timely deliveries
CLNT1017 | IJK Tech | Chloe Turner | 7778889991 | 021-77777779 | chloe.turner@example.com | 246 Maple St | Inactive | Contract renewal pending
CLNT1018 | LMN Enterprises | Liam Parker | 8889990002 | 021-88888890 | liam.parker@example.com | 987 Walnut St | Active | Reliable service
CLNT1019 | OPQ Innovations | Emma Wilson | 9990001113 | 021-99999902 | emma.wilson@example.com | 654 Cedar St | Active | Efficient communication
CLNT1020 | RST Enterprises | Ethan Smith | 1112224 | 021-00000013 | ethan.smith@example.com | 321 Elm St | Active | Positive feedback
CLNT1021 | STU Innovations | Olivia Garcia | 1112223334 | 021-11111112 | olivia.garcia@example.com | 369 Elm St | Active | Regular communication
CLNT1022 | UVW Enterprises | Ethan Adams | 2223334445 | 021-22222223 | ethan.adams@example.com | 789 Maple St | Active | Satisfied client
CLNT1023 | XYZ Solutions | Lily Turner | 3334445556 | 021-33333334 | lily.turner@example.com | 456 Oak St | Inactive | Contract ended
CLNT1024 | RST Tech | Noah Brown | 4445556667 | 021-44444445 | noah.brown@example.com | 101 Cedar St | Active | Excellent service
CLNT1025 | PQR Innovations | Ava Smith | 5556667778 | 021-55555556 | ava.smith@example.com | 246 Pine St | Active | Positive feedback
CLNT1026 | MNO Enterprises | Emma Wilson | 6667778889 | 021-66666667 | emma.wilson@example.com | 135 Walnut St | Active | Efficient communication
CLNT1027 | GHI Solutions | Ethan Parker | 7778889990 | 021-77777778 | ethan.parker@example.com | 246 Birch St | Inactive | Contract renewal pending
CLNT1028 | JKL Tech | Mia Turner | 8889990001 | 021-88888889 | mia.turner@example.com | 987 Cedar St | Active | Reliable service
CLNT1029 | DEF Enterprises | Liam Brown | 9990001112 | 021-99999901 | liam.brown@example.com | 654 Oak St | Active | Prompt responses
CLNT1030 | NOP Solutions | Noah Turner | 1112223 | 021-00000012 | noah.turner@example.com | 321 Maple St | Active | Quick problem resolution
CLNT1031 | ABC Corporation | John Doe | 1234567890 | 021-12345678 | john.doe@example.com | 123 Main Street | Active | Regular client
CLNT1032 | XYZ Ltd | Jane Smith | 2345678901 | 021-23456789 | jane.smith@example.com | 456 Elm Avenue | Active | New client
CLNT1033 | PQR Enterprises | David Johnson | 3456789012 | 021-34567890 | david.johnson@example.com | 789 Oak Lane | Active | Potential client
CLNT1034 | LMN Corporation | Sarah Brown | 4567890123 | 021-45678901 | sarah.brown@example.com | 101 Pine Street | Inactive | Contract expired
CLNT1035 | RST Ltd | Michael Wilson | 5678901234 | 021-56789012 | michael.wilson@example.com | 246 Cedar Road | Active | Satisfied customer
CLNT1036 | UVW Enterprises | Emily Taylor | 6789012345 | 021-67890123 | emily.taylor@example.com | 369 Walnut Avenue | Active | Regular communication
CLNT1037 | MNO Corporation | Daniel Martinez | 7890123456 | 021-78901234 | daniel.martinez@example.com | 987 Maple Street | Active | Reliable client
CLNT1038 | EFG Ltd | Olivia Anderson | 8901234567 | 021-89012345 | olivia.anderson@example.com | 654 Oak Street | Active | Responsive to queries
CLNT1039 | STU Enterprises | Ethan Garcia | 9012345678 | 021-90123456 | ethan.garcia@example.com | 321 Elm Lane | Active | Active collaboration
CLNT1040 | HIJ Corporation | Ava Thomas | 123456789 | 021-01234567 | ava.thomas@example.com | 543 Cedar Avenue | Active | Timely payments
CLNT1041 | LMN Enterprises | Jack Wilson | 1234567891 | 021-12345679 | jack.wilson@example.com | 789 Oak Street | Active | Responsive communication
CLNT1042 | OPQ Corporation | Lily Garcia | 2345678902 | 021-23456780 | lily.garcia@example.com | 456 Elm Avenue | Active | Regular updates
CLNT1043 | RST Enterprises | Noah Thompson | 3456789013 | 021-34567891 | noah.thompson@example.com | 101 Maple Lane | Active | Satisfied with services
CLNT1044 | STU Corporation | Emma Brown | 4567890124 | 021-45678902 | emma.brown@example.com | 246 Cedar Avenue | Inactive | Contract expired
CLNT1045 | TUV Enterprises | Ethan Miller | 5678901235 | 021-56789013 | ethan.miller@example.com | 369 Pine Street | Active | Excellent collaboration
CLNT1046 | UVW Corporation | Ava Wilson | 6789012346 | 021-67890124 | ava.wilson@example.com | 987 Walnut Avenue | Active | Positive feedback
CLNT1047 | VWX Enterprises | Mia Anderson | 7890123457 | 021-78901235 | mia.anderson@example.com | 654 Cedar Lane | Active | Reliable service
CLNT1048 | WXY Corporation | Oliver Thompson | 8901234568 | 021-89012346 | oliver.thompson@example.com | 321 Oak Street | Active | Efficient communication
CLNT1049 | XYZ Enterprises | Chloe Smith | 9012345679 | 021-90123457 | chloe.smith@example.com | 543 Pine Avenue | Active | Timely deliveries
CLNT1050 | YZA Corporation | Liam Wilson | 123456780 | 021-01234568 | liam.wilson@example.com | 765 Maple Road | Active | Regular client

## Projects
02. Project Details
Project ID | Project Title | Client | Description / Scope | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Project Lead (Internal) | Project Lead (Client) | Status
PRJ1001 | Data Analysis Project | XYZ Enterprises | Analyze and interpret data | 2030-08-01 | 2030-10-01 | 2030-08-05 | 2030-09-30 | Ethan Wilson | Olivia Miller | In Progress
PRJ1002 | Software Development | ABC Solutions | Develop custom software | 2030-09-01 | 2030-11-01 | 2030-09-05 | 2030-10-30 | Lily Thompson | Ethan Wilson | In Progress
PRJ1003 | Marketing Campaign | DEF Tech | Launch marketing campaign | 2030-10-01 | 2030-12-01 | 2030-10-05 | 2030-11-25 | Noah Brown | Lily Turner | In Progress
PRJ1004 | Website Redesign | GHI Innovations | Redesign corporate website | 2031-01-01 | 2031-03-01 | 2031-01-05 | 2031-02-25 | Ava Miller | Noah Brown | In Progress
PRJ1005 | IT Infrastructure Upgrade | JKL Enterprises | Upgrade IT infrastructure | 2031-02-01 | 2031-04-01 | 2031-02-05 | 2031-03-30 | Mia Garcia | Ava Smith | In Progress
PRJ1006 | App Development | MNO Solutions | Develop mobile application | 2031-03-01 | 2031-05-01 | 2031-03-05 | 2031-04-30 | Oliver Parker | Mia Turner | In Progress
PRJ1007 | Data Migration | PQR Tech | Migrate data to new platform | 2031-04-01 | 2031-06-01 | 2031-04-05 | 2031-05-30 | Chloe Thompson | Oliver Adams | In Progress
PRJ1008 | Marketing Analytics | STU Enterprises | Conduct marketing data analysis | 2031-05-01 | 2031-07-01 | 2031-05-05 | 2031-06-30 | Liam Wilson | Chloe Parker | In Progress
PRJ1009 | E-commerce Integration | VWX Innovations | Integrate e-commerce platform | 2031-06-01 | 2031-08-01 | 2031-06-05 | 2031-07-30 | Emma Thompson | Liam Brown | In Progress
PRJ1010 | Cloud Migration | YZ Tech | Migrate systems to cloud | 2031-07-01 | 2031-09-01 | 2031-07-05 | 2031-08-30 | Ethan Brown | Emma Wilson | In Progress
PRJ1011 | Data Analysis Project | QRS Solutions | Analyze and interpret data | 2029-08-01 | 2029-10-01 | 2029-08-05 | 2029-09-30 | Ethan Wilson | Ethan Miller | In Progress
PRJ1012 | Software Development | TUV Innovations | Develop custom software | 2029-09-01 | 2029-11-01 | 2029-09-05 | 2029-10-30 | Lily Thompson | Lily Garcia | In Progress
PRJ1013 | Marketing Campaign | WXY Enterprises | Launch marketing campaign | 2029-10-01 | 2029-12-01 | 2029-10-05 | 2029-11-25 | Noah Brown | Noah Turner | In Progress
PRJ1014 | Website Redesign | ZAB Tech | Redesign corporate website | 2030-01-01 | 2030-03-01 | 2030-01-05 | 2030-02-25 | Ava Miller | Ava Brown | In Progress
PRJ1015 | IT Infrastructure Upgrade | CDE Innovations | Upgrade IT infrastructure | 2030-02-01 | 2030-04-01 | 2030-02-05 | 2030-03-30 | Mia Garcia | Mia Smith | In Progress
PRJ1016 | App Development | FGH Solutions | Develop mobile application | 2030-03-01 | 2030-05-01 | 2030-03-05 | 2030-04-30 | Oliver Parker | Oliver Adams | In Progress
PRJ1017 | Data Migration | IJK Tech | Migrate data to new platform | 2030-04-01 | 2030-06-01 | 2030-04-05 | 2030-05-30 | Chloe Thompson | Chloe Turner | In Progress
PRJ1018 | Marketing Analytics | LMN Enterprises | Conduct marketing data analysis | 2030-05-01 | 2030-07-01 | 2030-05-05 | 2030-06-30 | Liam Wilson | Liam Parker | In Progress
PRJ1019 | E-commerce Integration | OPQ Innovations | Integrate e-commerce platform | 2030-06-01 | 2030-08-01 | 2030-06-05 | 2030-07-30 | Emma Thompson | Emma Wilson | In Progress
PRJ1020 | Cloud Migration | RST Enterprises | Migrate systems to cloud | 2030-07-01 | 2030-09-01 | 2030-07-05 | 2030-08-30 | Ethan Brown | Ethan Smith | In Progress
PRJ1021 | Data Analysis Project | STU Innovations | Analyze and interpret data | 2028-08-01 | 2028-10-01 | 2028-08-05 | 2028-09-30 | Olivia Adams | Olivia Garcia | In Progress
PRJ1022 | Software Development | UVW Enterprises | Develop custom software | 2028-09-01 | 2028-11-01 | 2028-09-05 | 2028-10-30 | Ethan Wilson | Ethan Adams | In Progress
PRJ1023 | Marketing Campaign | XYZ Solutions | Launch marketing campaign | 2028-10-01 | 2028-12-01 | 2028-10-05 | 2028-11-25 | Lily Thompson | Lily Turner | In Progress
PRJ1024 | Website Redesign | RST Tech | Redesign corporate website | 2029-01-01 | 2029-03-01 | 2029-01-05 | 2029-02-25 | Noah Garcia | Noah Brown | In Progress
PRJ1025 | IT Infrastructure Upgrade | PQR Innovations | Upgrade IT infrastructure | 2029-02-01 | 2029-04-01 | 2029-02-05 | 2029-03-30 | Ava Turner | Ava Smith | In Progress
PRJ1026 | App Development | MNO Enterprises | Develop mobile application | 2029-03-01 | 2029-05-01 | 2029-03-05 | 2029-04-30 | Emma Parker | Emma Wilson | In Progress
PRJ1027 | Data Migration | GHI Solutions | Migrate data to new platform | 2029-04-01 | 2029-06-01 | 2029-04-05 | 2029-05-30 | Ethan Thompson | Ethan Parker | In Progress
PRJ1028 | Marketing Analytics | JKL Tech | Conduct marketing data analysis | 2029-05-01 | 2029-07-01 | 2029-05-05 | 2029-06-30 | Mia Turner | Mia Turner | In Progress
PRJ1029 | E-commerce Integration | DEF Enterprises | Integrate e-commerce platform | 2029-06-01 | 2029-08-01 | 2029-06-05 | 2029-07-30 | Liam Garcia | Liam Brown | In Progress
PRJ1030 | Cloud Migration | NOP Solutions | Migrate systems to cloud | 2029-07-01 | 2029-09-01 | 2029-07-05 | 2029-08-30 | Noah Parker | Noah Turner | In Progress
PRJ1031 | Website Redesign | ABC Corporation | Redesign company website | 2024-03-01 | 2024-05-01 | 2024-03-05 | 2024-04-30 | Emily Brown | John Doe | In Progress
PRJ1032 | Marketing Campaign | XYZ Ltd | Launch marketing campaign | 2024-04-01 | 2024-06-01 | 2024-04-05 | 2024-05-30 | Michael Wilson | Jane Smith | In Progress
PRJ1033 | Product Development | PQR Enterprises | Develop new product | 2024-05-01 | 2024-07-01 | 2024-05-05 | 2024-06-30 | Daniel Martinez | David Johnson | In Progress
PRJ1034 | IT Infrastructure Upgrade | LMN Corporation | Upgrade IT infrastructure | 2024-06-01 | 2024-08-01 | 2024-06-05 | 2024-07-30 | Olivia Anderson | Sarah Brown | In Progress
PRJ1035 | Sales Training Program | RST Ltd | Conduct sales training program | 2024-07-01 | 2024-09-01 | 2024-07-05 | 2024-08-30 | Ethan Garcia | Michael Wilson | In Progress
PRJ1036 | App Development | UVW Enterprises | Develop mobile application | 2024-08-01 | 2024-10-01 | 2024-08-05 | 2024-09-30 | Ava Thomas | Emily Taylor | In Progress
PRJ1037 | Inventory Management | MNO Corporation | Implement inventory system | 2024-09-01 | 2024-11-01 | 2024-09-05 | 2024-10-30 | Daniel Martinez | Daniel Martinez | In Progress
PRJ1038 | Market Research | EFG Ltd | Conduct market research | 2024-10-01 | 2024-12-01 | 2024-10-05 | 2024-11-25 | Olivia Anderson | Olivia Anderson | In Progress
PRJ1039 | Website Development | STU Enterprises | Develop corporate website | 2024-11-01 | 2025-01-01 | 2024-11-05 | 2024-12-30 | Ethan Garcia | Ethan Garcia | In Progress
PRJ1040 | Social Media Campaign | HIJ Corporation | Launch social media campaign | 2024-12-01 | 2025-02-01 | 2024-12-05 | 2025-01-30 | Ava Thomas | Ava Thomas | In Progress
PRJ1041 | Content Marketing | LMN Enterprises | Launch content marketing campaign | 2025-01-01 | 2025-03-01 | 2025-01-05 | 2025-02-28 | Jack Wilson | Jack Wilson | In Progress
PRJ1042 | Product Launch | OPQ Corporation | Launch new product | 2025-02-01 | 2025-04-01 | 2025-02-05 | 2025-03-30 | Lily Garcia | Lily Garcia | In Progress
PRJ1043 | Website Development | RST Enterprises | Develop e-commerce website | 2025-03-01 | 2025-05-01 | 2025-03-05 | 2025-04-30 | Noah Thompson | Noah Thompson | In Progress
PRJ1044 | Sales Strategy | STU Corporation | Develop sales strategy | 2025-04-01 | 2025-06-01 | 2025-04-05 | 2025-05-30 | Emma Brown | Emma Brown | In Progress
PRJ1045 | IT System Integration | TUV Enterprises | Integrate IT systems | 2025-05-01 | 2025-07-01 | 2025-05-05 | 2025-06-30 | Ethan Miller | Ethan Miller | In Progress
PRJ1046 | Social Media Management | UVW Corporation | Manage social media accounts | 2025-06-01 | 2025-08-01 | 2025-06-05 | 2025-07-30 | Ava Wilson | Ava Wilson | In Progress
PRJ1047 | Inventory Optimization | VWX Enterprises | Optimize inventory management | 2025-07-01 | 2025-09-01 | 2025-07-05 | 2025-08-30 | Mia Anderson | Mia Anderson | In Progress
PRJ1048 | Market Analysis | WXY Corporation | Conduct market analysis | 2025-08-01 | 2025-10-01 | 2025-08-05 | 2025-09-30 | Oliver Thompson | Oliver Thompson | In Progress
PRJ1049 | Website Redesign | XYZ Enterprises | Redesign company website | 2025-09-01 | 2025-11-01 | 2025-09-05 | 2025-10-30 | Chloe Smith | Chloe Smith | In Progress
PRJ1050 | Training Program | YZA Corporation | Conduct employee training program | 2025-10-01 | 2025-12-01 | 2025-10-05 | 2025-11-25 | Liam Wilson | Liam Wilson | In Progress

## Tasks
03. Task Details
Task ID | Task Title | Client Name | Project Name | Task Description / Scope | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Assigned To | Assigned By | Status
T1001 | Data Transfer | XYZ Enterprises | Data Analysis Project | Transfer data to new platform | 2030-08-10 | 2030-08-15 | 2030-08-10 | 2030-08-14 | Ethan Turner | Ethan Wilson | In Progress
T1002 | App UI Design | ABC Solutions | Software Development | Design user interface for app | 2030-09-15 | 2030-09-20 | 2030-09-18 | 2030-09-20 | Chloe Thompson | Lily Thompson | In Progress
T1003 | Marketing Strategy Planning | DEF Tech | Marketing Campaign | Plan marketing strategy | 2030-10-20 | 2030-10-25 | 2030-10-22 | 2030-10-24 | Noah Brown | Noah Turner | In Progress
T1004 | Website Redesign Analysis | GHI Innovations | Website Redesign | Analyze current website | 2031-01-10 | 2031-01-15 | 2031-01-12 | 2031-01-14 | Ava Miller | Ava Brown | In Progress
T1005 | Infrastructure Assessment | JKL Enterprises | IT Infrastructure Upgrade | Assess current IT infrastructure | 2031-02-10 | 2031-02-15 | 2031-02-11 | 2031-02-14 | Mia Garcia | Mia Smith | In Progress
T1006 | App Development | MNO Solutions | App Development | Develop mobile application | 2031-03-10 | 2031-03-15 | 2031-03-10 | 2031-03-14 | Oliver Parker | Oliver Adams | In Progress
T1007 | Data Migration | PQR Tech | Data Migration | Migrate data to new platform | 2031-04-10 | 2031-04-15 | 2031-04-10 | 2031-04-14 | Lily Brown | Chloe Thompson | In Progress
T1008 | Marketing Data Analysis | STU Enterprises | Marketing Analytics | Analyze marketing data | 2031-05-10 | 2031-05-15 | 2031-05-12 | 2031-05-14 | Mia Parker | Mia Turner | In Progress
T1009 | E-commerce Integration | VWX Innovations | E-commerce Integration | Integrate e-commerce platform | 2031-06-10 | 2031-06-15 | 2031-06-10 | 2031-06-14 | Liam Smith | Emma Thompson | In Progress
T1010 | Cloud Migration | YZ Tech | Cloud Migration | Migrate systems to cloud | 2031-07-10 | 2031-07-15 | 2031-07-11 | 2031-07-14 | Ava Brown | Ethan Brown | In Progress
T1011 | Data Transfer | QRS Solutions | Data Analysis Project | Transfer data to new platform | 2029-08-10 | 2029-08-15 | 2029-08-10 | 2029-08-14 | Ethan Turner | Ethan Wilson | In Progress
T1012 | App UI Design | TUV Innovations | Software Development | Design user interface for app | 2029-09-15 | 2029-09-20 | 2029-09-18 | 2029-09-20 | Chloe Thompson | Lily Thompson | In Progress
T1013 | Marketing Strategy Planning | WXY Enterprises | Marketing Campaign | Plan marketing strategy | 2029-10-20 | 2029-10-25 | 2029-10-22 | 2029-10-24 | Noah Brown | Noah Turner | In Progress
T1014 | Website Redesign Analysis | ZAB Tech | Website Redesign | Analyze current website | 2030-01-10 | 2030-01-15 | 2030-01-12 | 2030-01-14 | Ava Miller | Ava Brown | In Progress
T1015 | Infrastructure Assessment | CDE Innovations | IT Infrastructure Upgrade | Assess current IT infrastructure | 2030-02-10 | 2030-02-15 | 2030-02-11 | 2030-02-14 | Mia Garcia | Mia Smith | In Progress
T1016 | App Development | FGH Solutions | App Development | Develop mobile application | 2030-03-10 | 2030-03-15 | 2030-03-10 | 2030-03-14 | Oliver Parker | Oliver Adams | In Progress
T1017 | Data Migration | IJK Tech | Data Migration | Migrate data to new platform | 2030-04-10 | 2030-04-15 | 2030-04-10 | 2030-04-14 | Lily Brown | Chloe Thompson | In Progress
T1018 | Marketing Data Analysis | LMN Enterprises | Marketing Analytics | Analyze marketing data | 2030-05-10 | 2030-05-15 | 2030-05-12 | 2030-05-14 | Mia Parker | Mia Turner | In Progress
T1019 | E-commerce Integration | OPQ Innovations | E-commerce Integration | Integrate e-commerce platform | 2030-06-10 | 2030-06-15 | 2030-06-10 | 2030-06-14 | Liam Smith | Emma Thompson | In Progress
T1020 | Cloud Migration | RST Enterprises | Cloud Migration | Migrate systems to cloud | 2030-07-10 | 2030-07-15 | 2030-07-11 | 2030-07-14 | Ava Brown | Ethan Brown | In Progress
T1021 | Data Transfer | STU Innovations | Data Analysis Project | Transfer data to new platform | 2028-08-10 | 2028-08-15 | 2028-08-10 | 2028-08-14 | Ethan Turner | Olivia Adams | In Progress
T1022 | App UI Design | UVW Enterprises | Software Development | Design user interface for app | 2028-09-15 | 2028-09-20 | 2028-09-18 | 2028-09-20 | Chloe Thompson | Ethan Wilson | In Progress
T1023 | Marketing Strategy Planning | XYZ Solutions | Marketing Campaign | Plan marketing strategy | 2028-10-20 | 2028-10-25 | 2028-10-22 | 2028-10-24 | Liam Brown | Lily Thompson | In Progress
T1024 | Website Redesign Analysis | RST Tech | Website Redesign | Analyze current website | 2029-01-10 | 2029-01-15 | 2029-01-12 | 2029-01-14 | Ava Miller | Noah Garcia | In Progress
T1025 | Infrastructure Assessment | PQR Innovations | IT Infrastructure Upgrade | Assess current IT infrastructure | 2029-02-10 | 2029-02-15 | 2029-02-11 | 2029-02-14 | Noah Brown | Ava Turner | In Progress
T1026 | App Development | MNO Enterprises | App Development | Develop mobile application | 2029-03-10 | 2029-03-15 | 2029-03-10 | 2029-03-14 | Ethan Parker | Emma Parker | In Progress
T1027 | Data Migration | GHI Solutions | Data Migration | Migrate data to new platform | 2029-04-10 | 2029-04-15 | 2029-04-10 | 2029-04-14 | Lily Brown | Ethan Thompson | In Progress
T1028 | Marketing Data Analysis | JKL Tech | Marketing Analytics | Analyze marketing data | 2029-05-10 | 2029-05-15 | 2029-05-12 | 2029-05-14 | Mia Parker | Mia Turner | In Progress
T1029 | E-commerce Integration | DEF Enterprises | E-commerce Integration | Integrate e-commerce platform | 2029-06-10 | 2029-06-15 | 2029-06-10 | 2029-06-14 | Liam Smith | Liam Garcia | In Progress
T1030 | Cloud Migration | NOP Solutions | Cloud Migration | Migrate systems to cloud | 2029-07-10 | 2029-07-15 | 2029-07-11 | 2029-07-14 | Ava Brown | Noah Parker | In Progress
T1031 | Content Creation | ABC Corporation | Website Redesign | Create content for new website | 2024-03-10 | 2024-03-15 | 2024-03-10 | 2024-03-14 | Emily Parker | Emily Brown | In Progress
T1032 | Social Media Strategy | XYZ Ltd | Marketing Campaign | Develop social media strategy | 2024-04-15 | 2024-04-20 | 2024-04-18 | 2024-04-20 | Michael Adams | Michael Wilson | In Progress
T1033 | Product Research | PQR Enterprises | Product Development | Conduct market research | 2024-05-20 | 2024-05-25 | 2024-05-22 | 2024-05-24 | Daniel Brown | Daniel Martinez | In Progress
T1034 | IT System Upgrade | LMN Corporation | IT Infrastructure Upgrade | Upgrade company's IT systems | 2024-06-10 | 2024-06-15 | 2024-06-10 | 2024-06-14 | Olivia Miller | Olivia Anderson | In Progress
T1035 | Training Material Development | RST Ltd | Sales Training Program | Develop training material | 2024-07-10 | 2024-07-15 | 2024-07-10 | 2024-07-14 | Ethan Thompson | Ethan Garcia | In Progress
T1036 | App Design | UVW Enterprises | App Development | Design UI/UX for mobile app | 2024-08-10 | 2024-08-15 | 2024-08-10 | 2024-08-14 | Ava Wilson | Ava Thomas | In Progress
T1037 | Inventory Setup | MNO Corporation | Inventory Management | Set up inventory system | 2024-09-10 | 2024-09-15 | 2024-09-10 | 2024-09-14 | Daniel Thompson | Daniel Martinez | In Progress
T1038 | Market Analysis | EFG Ltd | Market Research | Conduct market analysis | 2024-10-10 | 2024-10-15 | 2024-10-10 | 2024-10-14 | Olivia Brown | Olivia Anderson | In Progress
T1039 | Website Design | STU Enterprises | Website Development | Design website layout | 2024-11-10 | 2024-11-15 | 2024-11-10 | 2024-11-14 | Ethan Wilson | Ethan Garcia | In Progress
T1040 | Social Media Content | HIJ Corporation | Social Media Campaign | Create content for campaign | 2024-12-10 | 2024-12-15 | 2024-12-10 | 2024-12-14 | Ava Brown | Ava Thomas | In Progress
T1041 | Content Creation | LMN Enterprises | Content Marketing | Create content for campaign | 2025-01-10 | 2025-01-15 | 2025-01-10 | 2025-01-14 | Emily Wilson | Jack Wilson | In Progress
T1042 | Product Development | OPQ Corporation | Product Launch | Develop new product | 2025-02-15 | 2025-02-20 | 2025-02-18 | 2025-02-20 | Michael Garcia | Lily Garcia | In Progress
T1043 | Website Design | RST Enterprises | Website Development | Design website layout | 2025-03-20 | 2025-03-25 | 2025-03-22 | 2025-03-24 | Daniel Parker | Noah Thompson | In Progress
T1044 | Sales Strategy Development | STU Corporation | Sales Strategy | Develop sales strategy | 2025-04-10 | 2025-04-15 | 2025-04-10 | 2025-04-14 | Olivia Smith | Emma Brown | In Progress
T1045 | System Integration | TUV Enterprises | IT System Integration | Integrate IT systems | 2025-05-10 | 2025-05-15 | 2025-05-10 | 2025-05-14 | Ethan Wilson | Ethan Miller | In Progress
T1046 | Social Media Management | UVW Corporation | Social Media Management | Manage social media accounts | 2025-06-10 | 2025-06-15 | 2025-06-10 | 2025-06-14 | Ava Brown | Ava Wilson | In Progress
T1047 | Inventory Optimization | VWX Enterprises | Inventory Optimization | Optimize inventory management | 2025-07-10 | 2025-07-15 | 2025-07-10 | 2025-07-14 | Mia Anderson | Mia Anderson | In Progress
T1048 | Market Research | WXY Corporation | Market Analysis | Conduct market analysis | 2025-08-10 | 2025-08-15 | 2025-08-10 | 2025-08-14 | Oliver Brown | Oliver Thompson | In Progress
T1049 | Website Redesign | XYZ Enterprises | Website Redesign | Redesign company website | 2025-09-10 | 2025-09-15 | 2025-09-10 | 2025-09-14 | Chloe Wilson | Chloe Smith | In Progress
T1050 | Training Material Development | YZA Corporation | Training Program | Develop training material | 2025-10-10 | 2025-10-15 | 2025-10-10 | 2025-10-14 | Liam Brown | Liam Wilson | In Progress

## Employees
04. Employees
Employee ID | Name | Designation | Date of Joining | Status
E001 | Olivia Miller | Project Manager | 2030-01-15 | Active
E002 | Ethan Wilson | App Developer | 2029-03-20 | Active
E003 | Lily Turner | Marketing Manager | 2028-10-10 | Active
E004 | Noah Brown | Web Designer | 2027-05-05 | Active
E005 | Ava Smith | IT Specialist | 2026-09-30 | Active
E006 | Mia Turner | App Developer | 2025-07-15 | Active
E007 | Oliver Adams | Data Analyst | 2024-12-10 | Active
E008 | Chloe Parker | Marketing Analyst | 2023-11-01 | Active
E009 | Liam Brown | E-commerce Expert | 2022-08-20 | Active
E010 | Emma Wilson | Cloud Specialist | 2021-05-15 | Active
E011 | Ethan Wilson | Project Manager | 2029-01-15 | Active
E012 | Lily Thompson | App Developer | 2028-03-20 | Active
E013 | Noah Brown | Marketing Manager | 2027-10-10 | Active
E014 | Ava Miller | Web Designer | 2026-05-05 | Active
E015 | Mia Garcia | IT Specialist | 2025-09-30 | Active
E016 | Oliver Parker | App Developer | 2024-07-15 | Active
E017 | Chloe Thompson | Data Analyst | 2023-12-10 | Active
E018 | Mia Parker | Marketing Analyst | 2022-11-01 | Active
E019 | Liam Smith | E-commerce Expert | 2021-08-20 | Active
E020 | Ava Brown | Cloud Specialist | 2020-05-15 | Active
E021 | Olivia Adams | Project Manager | 2028-01-15 | Active
E022 | Ethan Wilson | App Developer | 2027-03-20 | Active
E023 | Lily Thompson | Marketing Manager | 2026-10-10 | Active
E024 | Noah Garcia | Web Designer | 2025-05-05 | Active
E025 | Ava Turner | IT Specialist | 2024-09-30 | Active
E026 | Emma Parker | App Developer | 2023-07-15 | Active
E027 | Ethan Thompson | Data Analyst | 2022-12-10 | Active
E028 | Mia Parker | Marketing Analyst | 2021-11-01 | Active
E029 | Liam Smith | E-commerce Expert | 2020-08-20 | Active
E030 | Ava Brown | Cloud Specialist | 2019-05-15 | Active
E031 | Emily Brown | Manager | 2022-05-01 | Active
E032 | Michael Adams | Marketing | 2022-06-15 | Active
E033 | Daniel Brown | Analyst | 2022-07-10 | Active
E034 | Ethan Thompson | Sales | 2022-09-20 | Active
E035 | Ava Wilson | Designer | 2022-10-15 | Active
E036 | Daniel Thompson | Technician | 2022-11-10 | Active
E037 | Olivia Brown | Researcher | 2022-12-05 | Active
E038 | Ethan Wilson | Consultant | 2023-01-01 | Active
E039 | Ava Brown | Coordinator | 2023-02-15 | Active
E040 | Emily Wilson | Manager | 2023-05-01 | Active
E041 | Michael Garcia | Marketing | 2023-06-15 | Active
E042 | Daniel Parker | Analyst | 2023-07-10 | Active
E043 | Olivia Smith | Developer | 2023-08-05 | Active
E044 | Ethan Wilson | Sales | 2023-09-20 | Active
E045 | Ava Brown | Designer | 2023-10-15 | Active
E046 | Mia Anderson | Technician | 2023-11-10 | Active
E047 | Oliver Brown | Researcher | 2023-12-05 | Active
E048 | Chloe Wilson | Consultant | 2024-01-01 | Active
E049 | Liam Brown | Coordinator | 2024-02-15 | Active

## Resourcing
05. Resourcing
Project ID | Project Name | Employee ID | Employee Name | Start Date | End Date | Expected Hours
PRJ1001 | Data Analysis Project | E001 | Olivia Miller | 2030-08-01 | 2030-10-01 | 150
PRJ1002 | Software Development | E002 | Ethan Wilson | 2030-09-01 | 2030-11-01 | 120
PRJ1003 | Marketing Campaign | E003 | Lily Turner | 2030-10-01 | 2030-12-01 | 100
PRJ1004 | Website Redesign | E004 | Noah Brown | 2031-01-01 | 2031-03-01 | 130
PRJ1005 | IT Infrastructure Upgrade | E005 | Ava Smith | 2031-02-01 | 2031-04-01 | 140
PRJ1006 | App Development | E006 | Mia Turner | 2031-03-01 | 2031-05-01 | 110
PRJ1007 | Data Migration | E007 | Oliver Adams | 2031-04-01 | 2031-06-01 | 120
PRJ1008 | Marketing Analytics | E008 | Chloe Parker | 2031-05-01 | 2031-07-01 | 110
PRJ1009 | E-commerce Integration | E009 | Liam Brown | 2031-06-01 | 2031-08-01 | 130
PRJ1010 | Cloud Migration | E010 | Emma Wilson | 2031-07-01 | 2031-09-01 | 140
PRJ1011 | Data Analysis Project | E011 | Ethan Wilson | 2029-08-01 | 2029-10-01 | 150
PRJ1012 | Software Development | E012 | Lily Thompson | 2029-09-01 | 2029-11-01 | 120
PRJ1013 | Marketing Campaign | E013 | Noah Brown | 2029-10-01 | 2029-12-01 | 100
PRJ1014 | Website Redesign | E014 | Ava Miller | 2030-01-01 | 2030-03-01 | 130
PRJ1015 | IT Infrastructure Upgrade | E015 | Mia Garcia | 2030-02-01 | 2030-04-01 | 140
PRJ1016 | App Development | E016 | Oliver Parker | 2030-03-01 | 2030-05-01 | 110
PRJ1017 | Data Migration | E017 | Chloe Thompson | 2030-04-01 | 2030-06-01 | 120
PRJ1018 | Marketing Analytics | E018 | Mia Parker | 2030-05-01 | 2030-07-01 | 110
PRJ1019 | E-commerce Integration | E019 | Liam Smith | 2030-06-01 | 2030-08-01 | 130
PRJ1020 | Cloud Migration | E020 | Ava Brown | 2030-07-01 | 2030-09-01 | 140
PRJ1021 | Data Analysis Project | E021 | Olivia Adams | 2028-08-01 | 2028-10-01 | 150
PRJ1022 | Software Development | E022 | Ethan Wilson | 2028-09-01 | 2028-11-01 | 120
PRJ1023 | Marketing Campaign | E023 | Lily Thompson | 2028-10-01 | 2028-12-01 | 100
PRJ1024 | Website Redesign | E024 | Noah Garcia | 2029-01-01 | 2029-03-01 | 130
PRJ1025 | IT Infrastructure Upgrade | E025 | Ava Turner | 2029-02-01 | 2029-04-01 | 140
PRJ1026 | App Development | E026 | Emma Parker | 2029-03-01 | 2029-05-01 | 110
PRJ1027 | Data Migration | E027 | Ethan Thompson | 2029-04-01 | 2029-06-01 | 120
PRJ1028 | Marketing Analytics | E028 | Mia Parker | 2029-05-01 | 2029-07-01 | 110
PRJ1029 | E-commerce Integration | E029 | Liam Smith | 2029-06-01 | 2029-08-01 | 130
PRJ1030 | Cloud Migration | E030 | Ava Brown | 2029-07-01 | 2029-09-01 | 140
PRJ1031 | Website Redesign | E031 | Emily Brown | 2024-03-05 | 2024-04-30 | 80
PRJ1032 | Marketing Campaign | E032 | Michael Adams | 2024-04-05 | 2024-05-30 | 100
PRJ1033 | Product Development | E033 | Daniel Brown | 2024-05-05 | 2024-06-30 | 120
PRJ1034 | IT Infrastructure Upgrade | E001 | Olivia Miller | 2024-06-05 | 2024-07-30 | 80
PRJ1035 | Sales Training Program | E034 | Ethan Thompson | 2024-07-05 | 2024-08-30 | 100
PRJ1036 | App Development | E035 | Ava Wilson | 2024-08-05 | 2024-09-30 | 120
PRJ1037 | Inventory Management | E036 | Daniel Thompson | 2024-09-05 | 2024-10-30 | 80
PRJ1038 | Market Research | E037 | Olivia Brown | 2024-10-05 | 2024-11-25 | 100
PRJ1039 | Website Development | E038 | Ethan Wilson | 2024-11-05 | 2024-12-30 | 120
PRJ1040 | Social Media Campaign | E039 | Ava Brown | 2024-12-05 | 2025-01-30 | 100
PRJ1041 | Content Marketing | E040 | Emily Wilson | 2025-01-05 | 2025-02-28 | 80
PRJ1042 | Product Launch | E041 | Michael Garcia | 2025-02-05 | 2025-03-30 | 100
PRJ1043 | Website Development | E042 | Daniel Parker | 2025-03-05 | 2025-04-30 | 120
PRJ1044 | Sales Strategy | E043 | Olivia Smith | 2025-04-05 | 2025-05-30 | 80
PRJ1045 | IT System Integration | E044 | Ethan Wilson | 2025-05-05 | 2025-06-30 | 100
PRJ1046 | Social Media Management | E045 | Ava Brown | 2025-06-05 | 2025-07-30 | 120
PRJ1047 | Inventory Optimization | E046 | Mia Anderson | 2025-07-05 | 2025-08-30 | 80
PRJ1048 | Market Analysis | E047 | Oliver Brown | 2025-08-05 | 2025-09-30 | 100
PRJ1049 | Website Redesign | E048 | Chloe Wilson | 2025-09-05 | 2025-10-30 | 120
PRJ1050 | Training Program | E049 | Liam Brown | 2025-10-05 | 2025-11-25 | 100